## Initial Risk Model
Initial Risk Model
2023-08-25
No. | Risk Name / Category | Date Raised | Risk Area | Risk Description What is the specific risk to your business objective? | Causes What might cause the risk to occur? (internal and external causes of the risk) | Consequences What are the possible outcomes if the risk occurred? | Inherent Risk (Before Controls) |  |  | Existing Controls What controls do you currently have in place to manage the risk? | Control Effectiveness Rating | Residual Risk (After existing controls) |  |  | Risk Improvement Plan What additional action (if any) should be taken to further manage this risk? | Target Date | Target Risk (After risk improvement, if any)
[7 empty] | Likelihood | Impact | Risk Rating |  |  | Likelihood | Impact | Risk Rating |  |  | Likelihood | Impact | Risk Rating
1 | Earthquake | 2023-08-25 | Business and personal | An earthquake of .7 magnitude or higher causing severe damage. |  | Property/equipment damage, power outage, potential loss of life and data. | Rare | Catastrophic | High | [5 empty] | Keep virtual copies. | 2023-09-08 | Rare | Major | Medium
2 | Inadequate skills | 2023-08-25 | Personal | Unable to complete a task/objective | Lack of knowledge | Loss of time | Happened | Minor | Medium | A strong willingness to learn, academic and industry support. | Effective | Almost certain | Insignificant | Medium
3 | Data exposure | 2023-08-25 | Business | Sensitive customer data gets exposed | Weak password, threat actor, data leak | Loss of time, damage to public image | Rare | Major | Medium
4 | Catching Covid/cold | 2023-08-25 | Personal |  | Public places, low temperatures | Loss of time | Happened | Minor | Medium | Wear a mask when needed, cleanliness | Partially effective | Unlikely | Moderate | Medium
5 | Progress loss | 2023-08-25 | Business and Academic |  | Corruption, hardware failure, accidental deletion | Loss of resouces and time | Possible | Moderate | Medium | [5 empty] | Keep additional copies | 2023-09-08 | Rare | Minor | Low
6 | Academic Work Overload | 2023-10-12 | Academic | Having to finish multiple academic tasks within a small timeframe. | High academic workload | High stress and limited industry work | Happened | Moderate | High | Spend what time I can, when I can, doing what I can | Ineffective | Almost certain | Moderate | High

## Halfway Risk Model (2)
Halfway Risk Model
2023-10-12
No. | Risk Name / Category | Date Raised | Risk Area | Risk Description What is the specific risk to your business objective? | Causes What might cause the risk to occur? (internal and external causes of the risk) | Consequences What are the possible outcomes if the risk occurred? | Inherent Risk (Before Controls) |  |  | Existing Controls What controls do you currently have in place to manage the risk? | Control Effectiveness Rating | Residual Risk (After existing controls) |  |  | Risk Improvement Plan What additional action (if any) should be taken to further manage this risk? | Target Date | Target Risk (After risk improvement, if any)
[7 empty] | Likelihood | Impact | Risk Rating |  |  | Likelihood | Impact | Risk Rating |  |  | Likelihood | Impact | Risk Rating
1 | Earthquake | 2023-08-25 | Business and personal | An earthquake of .7 magnitude or higher causing severe damage. |  | Property/equipment damage, power outage, potential loss of life and data. | Rare | Catastrophic | High | [5 empty] | Keep virtual copies. | 2023-09-08 | Rare | Major | Medium
2 | Inadequate skills | 2023-08-25 | Personal | Unable to complete a task/objective | Lack of knowledge | Loss of time | Happened | Minor | Medium | A strong willingness to learn, academic and industry support. | Effective | Almost certain | Insignificant | Medium
3 | Data exposure | 2023-08-25 | Business | Sensitive customer data gets exposed | Weak password, threat actor, data leak | Loss of time, damage to public image | Rare | Major | Medium
4 | Catching Covid/cold | 2023-08-25 | Personal |  | Public places, low temperatures | Loss of time | Happened | Minor | Medium | Wear a mask when needed, cleanliness | Partially effective | Unlikely | Moderate | Medium
5 | Progress loss | 2023-08-25 | Business and Academic |  | Corruption, hardware failure, accidental deletion | Loss of resouces and time | Possible | Moderate | Medium | [5 empty] | Keep additional copies | 2023-09-08 | Rare | Minor | Low
6 | Academic Work Overload | 2023-10-12 | Academic | Having to finish multiple academic tasks within a small timeframe. | High academic workload | High stress and limited industry work | Happened | Moderate | High | Spend what time I can, when I can, doing what I can | Ineffective | Almost certain | Moderate | High

## Final Risk Model
Final Risk Model
2023-11-28
No. | Risk Name / Category | Date Raised | Risk Area | Risk Description What is the specific risk to your business objective? | Causes What might cause the risk to occur? (internal and external causes of the risk) | Consequences What are the possible outcomes if the risk occurred? | Inherent Risk (Before Controls) |  |  | Existing Controls What controls do you currently have in place to manage the risk? | Control Effectiveness Rating | Residual Risk (After existing controls) |  |  | Risk Improvement Plan What additional action (if any) should be taken to further manage this risk? | Target Date | Target Risk (After risk improvement, if any)
[7 empty] | Likelihood | Impact | Risk Rating |  |  | Likelihood | Impact | Risk Rating |  |  | Likelihood | Impact | Risk Rating
1 | Earthquake | 2023-08-25 | Business and personal | An earthquake of .7 magnitude or higher causing severe damage. |  | Property/equipment damage, power outage, potential loss of life and data. | Rare | Catastrophic | High | [5 empty] | Keep virtual copies. | Continuous | Rare | Major | Medium
2 | Inadequate skills/knowledge | 2023-08-25 | Personal | Unable to complete a task/objective, | Lack of skills/knowledge in certain areas | Loss of time | Happened | Major | Critical | A strong willingness to learn, academic and industry support. | Partially effective | Almost certain | Major | Critical
3 | Data exposure | 2023-08-25 | Business | Sensitive customer data gets exposed | Weak password, threat actor, data leak | Loss of time, damage to public image | Rare | Major | Medium
4 | Catching Covid/cold | 2023-08-25 | Personal |  | Public places, low temperatures | Loss of time | Happened | Minor | Medium | Wear a mask when needed, cleanliness | Partially effective | Unlikely | Moderate | Medium
5 | Progress loss | 2023-08-25 | Business and Academic |  | Corruption, hardware failure, accidental deletion | Loss of resouces and time | Possible | Moderate | Medium | [5 empty] | Keep additional copies, backup and save frequently | Continuous | Rare | Minor | Low
6 | Academic Work Overload | 2023-10-12 | Academic | Having to finish multiple academic tasks within a small timeframe. | High academic workload | High stress and limited industry work | Happened | Moderate | High | Spend what time I can, when I can, doing what I can | Ineffective | Almost certain | Moderate | High

## Dropdown lists
Happened | Catastrophic | Critical | Effective |  | Insignificant | Minor | Moderate | Major | Catastrophic
Almost certain | Major | High | Partially effective | Happened | Medium | Medium | High | Critical | Critical
Likely | Moderate | Medium | Ineffective | Almost certain | Medium | Medium | High | Critical | Critical
Possible | Minor | Low |  | Likely | Medium | Medium | High | High | Critical
Unlikely | Insignificant |  |  | Possible | Medium | Medium | Medium | High | Critical
Rare |  |  |  | Unlikely | Low | Medium | Medium | High | High
|  |  |  | Rare | Low | Low | Medium | Medium | High