## Academic Timeline
Week | Task | Hours Spent | Weekday | Notes |  |  |  | Assessment | Percentage | Total percentage | Pass criteria
1 | Class | 4 | [5 empty] | A1 | 50% | 5% | 50%
1 | CV | 4 |  | Created cv, got feadback, completed some changes |  |  |  | A2
1 | Project Analysis | 3 |  | Analysed WellNow and Hail Project Briefs |  |  |  | A3 |  |  | 50%
1 | Study | 2 |  | Course outline, veiwing weekly material |  | 13
2 | Hail Cover letter creation | 3
2 | Class | 4
2 | Interview | 3 |  | Prep time/furthar study included |  | 10
3 | Class | 4
3 | Project Analysis | 4 |  | Analysed 5 more project briefs
3 | Noria, Treat NZ cover letters | 3 |  |  |  | 11
4 | Class | 3 |  | Interview reduced class time by 1 hour
4 | Interview | 3 |  | Prep time/furthar study included
4 | Project proposal | 3 |  | Gathering information, Looking at class material |  | 9
5 | Class | 4
5 | Project proposal | 26 |  |  |  | 30
6 | Project proposal | 6 | Monday
6 | Time tracking | 1
6 | Meetings | 2 | Mon, Tue, Thur | Progress check |  | 9
7 | Time tracking | 1
7 | Weekly meeting | 0.5 | Thursday |  |  | 1.5
8 | Class | 2 | Monday
8 | Time tracking | 1 |  |  |  | 3
9 | Portfolio changes | 4 | Monday
9 | Weekly sign-off forms | 2 | Thursday
9 | Meetings | 1.5 | Thursday, Friday |  |  | 8.5
9 | Time tracking | 1
Break 1 | Weekly sign-off forms | 0.5 | Monday
Break 1 | Halfway Reports | 2 | Tuesday
Break 1 | Emerge Personal Profile Statement | 1.5 | Wednesday
Break 1 | Time tracking | 1
Break 1 | Halfway Reports | 3 | Wednesday
Break 1 | Weekly meeting | 0.5 | Thursday
Break 1 | Halfway Reports | 4 | Thursday |  |  | 12.5
Break 2 | Weekly sign-off forms | 0.5 | Wednesday |  |  |  | 178
Break 2 | Halfway Reports | 2 | Wednesday
Break 2 | Weekly meeting | 0.5 | Thursday
Break 2 | Time tracking | 1 |  |  |  | 4
10 | Class, Emerge photo | 2.5 | Monday
10 | Methodology essay | 3 | Tuesday
10 | Halfway Reports | 2 | Tuesday
10 | Halfway Reports, Emerge Statement | 3 | Wednesday
10 | Halfway Reports | 4 | Thursday
10 | Time tracking | 1
10 | Weekly sign-off forms | 0.5 | Thursday |  |  | 16
11 | Class | 2 | Monday
11 | Weekly sign-off forms | 0.5 | Wednesday
11 | Weekly meeting | 0.5 | Thursday
11 | Time tracking | 1 |  |  |  | 4
12 | Weekly sign-off forms | 0.5 | Wednesday
12 | Weekly meeting | 0.5 | Thursday
12 | Time tracking | 1 |  |  |  | 2
13 | Class | 2 | Monday
13 | Weekly sign-off forms | 0.5 | Wednesday
13 | Poster | 2 | Wednesday
13 | Poster | 1.5 | Thursday
13 | Weekly meeting | 0.5 | Thursday
13 | Time tracking | 1 |  |  |  | 7.5
14 | Class | 2 | Monday
14 | Weekly sign-off forms | 0.5 | Wednesday
14 | Weekly meeting | 0.5 | Thursday
14 | Class | 2 | Thursday
14 | Time tracking | 1 |  |  |  | 6
15 | Weekly sign-off forms | 0.5 | Wednesday
15 | Weekly meeting | 0.5 | Thursday
15 | Time tracking | 1 |  |  |  | 2
16 | Meetings | 1 | Monday, Friday
16 | Time tracking | 0.5
16 | Weekly sign-off | 0.5 | Monday
16 | Retrieving Information | 8 | Tuesday, Wednesday | Needed to grab information before my permissions where removed
16 | Final Report | 6 | Thursday | Executive Summary, started project details
16 | Final Report | 5 | Friday | Ethics, Sustainability, Elevator pitch
16 | Final Report, Poster | 8 | Saturday, Sunday | Student skills, Stakeholders Poster
17
29

## Industry Timeline
IND Week | Task | Hours Spent | Weekday | Notes
1 | Scrum meeting | 0.5 | Monday |  | Hours Remaining: |  | 0
1 | API Research | 1.5 | Tuesday
1 | Nookal Research | 1.5 | Tuesday
1 | API Research | 3 | Wednesday
1 | API Research | 3.5 | Thursday
1 | System comprehension | 2 | Thursday
1 | SEO Improvements | 4 | Friday | Practice Pages, Speciality pages | 16
2 | Scrum meeting | 0.5 | Monday
2 | API Research | 4.5 | Monday
2 | SEO | 2 | Monday
2 | Nookal site options | 3.5 | Tuesday
2 | wsl | 1 | Tuesday
2 | wsl | 1 | Wednesday
2 | Setmore site options | 2.5 | Wednesday
2 | Acuity site options | 2 | Wednesday
2 | Ruby | 5 | Thursday | Installation, learning | 22 |  | 38
3 | Scrum meeting | 0.5 | Monday
3 | SEO Improvements | 2.5 | Tuesday | Completing content, researching styles
3 | API research | 3 | Tuesday | Understanding how to use APIs (Insomnia)
3 | API Work | 2 | Wednesday
3 | Research | 2 | Wednesday | VS code extension and shortcuts, API key connections Basic Auth, Oauth
3 | SEO Improvements | 4 | Friday | Content creation, call with Luke
3 | Research | 5 | Sunday | React, Tailwind css | 19 |  | 115.5 | 184.5
4 | SEO Improvements | 5.5 | Tuesday | Learning React, changing html code to React
4 | React/Enviroment setup | 5 | Wednesday | Learning React, setting up the front-end and back-end on Visual Studio Code with Luke
4 | SEO Improvements | 3 | Thursday | Experimenting with features in React
4 | SEO Improvements | 3 | Friday | Creating Frequently Asked Questions sections
4 | SEO Improvements | 3.5 | Saturday | Flexbox, Links, Tailwind css
4 | SEO Improvements | 3 | Sunday | Specialties page, cleaning code, breadcrumbs | 23
5 | Scrum | 1 | Monday | Meeting, Sprint retrospecive
5 | SEO Improvements | 4 | Monday | Styling, layout changes, links
5 | SEO Improvements | 3 | Tuesday | React, making changes with Luke
5 | SEO Improvements | 2 | Wednesday | Fixing bugs, improving code
5 | SEO Improvements | 1 | Thursday | Design, code analysis | 14
5 | SEO Improvements | 3 | Friday | Design improvements, React code analysis
6 | Scrum | 0.5 | Monday
6 | SEO Improvements | 4.5 | Monday | Design improvements, pull request
6 | SEO Improvements | 5.5 | Tuesday | Design improvements, Services search results, pull request
6 | SEO Improvements | 3.5 | Wednesday | Updating content, styling changes
6 | Slack Call | 2 | Wednesday | Extesnsions, search results
6 | SEO Improvements | 2.5 | Thursday | Feedback, seo research | 21.5
6 | SEO Improvements | 3 | Friday | Background changes, content changes
7 | Scrum | 1 | Monday | Meeting, Sprint retrospective |  | no time sheets
7 | SEO Improvements | 5.5 | Monday | Practices pages structuring
7 | SEO Improvements | 6 | Tuesday | Services pages content, services pages styling
7 | SEO Improvements | 4.5 | Friday | business api | 17
8 | Scrum | 0.5 | Monday
8 | SEO Improvements | 4.5 | Monday | Setting up test data
8 | SEO Improvements | 7 | Tuesday | Practitioner index page
8 | SEO Improvements | 8 | Wednesday | Grouping clinics by city, manipulating test data
8 | SEO Improvements | 6.5 | Thursday | Manipulating test data, implementing search bar
8 | SEO Improvements | 5 | Friday | Adding information to Clinic specific pages | 40.5 | 57.5
8 | SEO Improvements | 5 | Saturday | Formatting components and code
8 | SEO Improvements | 4 | Sunday | Designing Clinic specific pages
9 | SEO Improvements | 7 | Tuesday | Research on react
9 | SEO Improvements | 8 | Tuesday | Slack communication with Niamh, Sam, Luke, and Henry. Sorting practitioner and clinic data.
9 | SEO Improvements | 8 | Wednesday | Researched and tried parsing data through multiple methods, figuring out data handling and list formatting
9 | SEO Improvements | 8.5 | Thursday | Researched Pagination, sorted cities and clinic names alphabetically, implemented show more to clinic names limiting it to 10.
9 | SEO Improvements | 3 | Friday | Attempting to pass data
9 | API | 4 | Friday | Analysing existing APIs, connecting to Nookal and Setmore, retrieving data | 38.5
10 | Scrum | 0.5 | Monday
10 | API | 5 | Monday
10 | API | 6 | Tuesday
10 | SEO Improvements | 6 | Wednesday
10 | SEO Improvements | 6 | Thursday | Creating is valid checker
10 | SEO Improvements | 5 | Friday | Calls with Luke and Henry
10 |  | 1 | Sunday | Fixing bundle install | 29.5
11 | Scrum | 1.5 | Monday | Meeting, Sprint retrospective, Planning the sprint
11 | SEO Improvements | 4 | Monday
11 | SEO Improvements | 5 | Tuesday
11 | SEO Improvements | 4 | Wednesday
11 | API | 4 | Thursday | Research
11 | SEO Improvements | 4 | Friday
11 | SEO Improvements | 4 | Saturday | Research on react | 26.5
12 | Scrum | 0.5 | Monday
12 | SEO Improvements | 3 | Monday
12 | SEO Improvements | 5 | Tuesday
12 | SEO Improvements | 6 | Wednesday | Worked on creating the APIs for the practices pages and had a paired code review with Luke.
12 | SEO Improvements | 6 | Thursday | Researched svg and styling tips, attempted to create a svg.
12 | SEO Improvements | 4 | Friday | Changing styles
12 | SEO Improvements | 2 | Saturday | Changing styles
12 | SEO Improvements | 3 | Sunday | Changing styles | 29.5
13 | Wrapping up | 3 | Monday | Final design review, instructions on what needs to be done going forward, notes on what has been done, meeting, and sprint retrospective. | 3 |  | 184.5
300

## Burndowns
KEY
Burndown Chart
Industry Burndown
[5 empty] | Hours per week |  | Remaining hours
| Academic Week | Starting week date | Sprint Number | Deliverable | Planned | Actual | Planned | Actual
| 1 | 2023-07-24 |  |  | 0 | 0 | 300 | 300
| 2 | 2023-07-31 |  |  | 0 | 0 | 300 | 300
| 3 | 2023-08-07 |  |  | 0 | 0 | 300 | 300
| 4 | 2023-08-14 |  |  | 0 | 0 | 300 | 300
| 5 | 2023-08-21 |  |  | 0 | 0 | 300 | 300
| 6 | 2023-08-28 | Project start/Sprint 1 | Research | 25 | 16 | 275 | 284
| 7 | 2023-09-04 | Sprint 1 | Research | 25 | 22 | 250 | 262
| 8 | 2023-09-11 | Sprint 2 | SEO Improvements Services Pages | 25 | 19 | 225 | 243
| 9 | 2023-09-18 | Sprint 2 | SEO Improvements Services Pages | 25 | 23 | 200 | 220
| Break Week 1 | 2023-09-25 | Sprint 3 | SEO Improvements Services Pages | 25 | 14 | 175 | 206
| Break Week 2 | 2023-10-02 | Sprint 3 | SEO Improvements Services Pages | 25 | 21.5 | 150 | 184.5
| 10 | 2023-10-09 | Sprint 4 | SEO Improvements Practices Pages | 25 | 17 | 125 | 167.5
| 11 | 2023-10-16 | Sprint 4 | SEO Improvements Practices Pages | 25 | 40.5 | 100 | 127
| 12 | 2023-10-23 | Sprint 5 | SEO Improvements Practices Pages | 25 | 38.5 | 75 | 88.5
| 13 | 2023-10-30 | Sprint 5 | SEO Improvements Practices Pages | 25 | 29.5 | 50 | 59
| 14 | 2023-11-06 | Sprint 6 | SEO Improvements Practices Pages | 25 | 26.5 | 25 | 32.5
| 15 | 2023-11-13 | Sprint 6 | SEO Improvements Practices Pages | 25 | 29.5 | 0 | 3
| 16 | 2023-11-20 | Project finish | Wrapping up | 0 | 3 | 0 | 0
|  |  |  | Total Industry Hours: | 300 | 300
[5 empty] | weekly | 35
Academic Burndown
[5 empty] | Hours per week |  | Remaining Hours
| Academic Week | Starting week date | Project Stage | Deliverable | Planned | Actual | Planned | Actual
| 1 | 2023-07-24 |  | Class Start | 11 | 13 | 150 | 150
| 2 | 2023-07-31 |  |  | 9 | 10 | 139 | 137
| 3 | 2023-08-07 |  |  | 9 | 11 | 130 | 127
| 4 | 2023-08-14 |  |  | 9 | 9 | 121 | 116
| 5 | 2023-08-21 |  | Proposal | 16 | 30 | 112 | 107
| 6 | 2023-08-28 | Project start/Sprint 1 |  | 2 | 9 | 96 | 77
| 7 | 2023-09-04 | Sprint 1 | Proposal Submission | 2 | 1.5 | 94 | 68
| 8 | 2023-09-11 | Sprint 2 |  | 4 | 3 | 92 | 66.5
| 9 | 2023-09-18 | Sprint 2 |  | 4 | 8.5 | 88 | 63.5
| Break Week 1 | 2023-09-25 | Sprint 3 |  | 15 | 12.5 | 84 | 55
| Break Week 2 | 2023-10-02 | Sprint 3 |  | 4 | 4 | 69 | 42.5
| 10 | 2023-10-09 | Half-way/Sprint 4 | Half-way Reports | 4 | 16 | 65 | 38.5
| 11 | 2023-10-16 | Sprint 4 |  | 4 | 4 | 61 | 22.5
| 12 | 2023-10-23 | Sprint 5 |  | 4 | 2 | 57 | 18.5
| 13 | 2023-10-30 | Project finish/Sprint 5 |  | 12 | 7.5 | 53 | 16.5
| 14 | 2023-11-06 |  | Final Reports, | 12 | 6 | 41 | 9
| 15 | 2023-11-13 |  | Poster, Short paper, | 12 | 29 | 29 | 3
| 16 | 2023-11-20 |  | Methodology Essay | 12 | 20 | 17 | -26
| 17 | 2023-11-27 |  | & Panel | 3 | 2 | 5 | -46
| EMERGE 18 | 2023-12-04 |  | Emerge | 2 | 2 | 2 | -48 | 73
|  |  |  | Total Academic Hours: | 150 | 200 | 0 | -50
weekly
| I&A Total Hours: | 500
| Expected total: | 450
| Total Remaining: | -50

## Meetings
AC Supiervisor Meetings
Description | Date | Time | Particapants
Proposal check | 2023-08-30 | 12pm | Rob, Brock
Proposal check | 2023-08-31 | 11am | Rob, Brock
Proposal check | 2023-09-06 | 12pm | Rob, Brock
Weekly Meeting | 2023-09-21 | 12pm | Rob, Brock
Weekly Meeting | 2023-09-28 | 12pm | Rob, Brock
Weekly Meeting | 2023-10-05 | 12pm | Rob, Brock
Weekly Meeting | 2023-10-12 | 12pm | Rob, Brock
Weekly Meeting | 2023-10-19 | 12pm | Rob, Brock
Weekly Meeting | 2023-10-26 | 12pm | Rob, Brock
Weekly Meeting | 2023-11-02 | 12pm | Rob, Brock
Weekly Meeting | 2023-11-09 | 12pm | Rob, Brock
Weekly Meeting | 2023-11-16 | 12pm | Rob, Brock
IND Work Update | 2023-11-20 | 1.30pm | Rob, Brock
Academic Status Meeting | 2023-11-24 | 1pm | Rob, Brock |  | Panel Presentaion
Final Meeting | 2023-11-28 | 1pm | Rob, Brock |  | Date | Time | Location | Particapants
[5 empty] | 2023-12-01 | 9am-10:30am | X206 | David, Henry, Robert, Brock, Melanie
IND Dev Team Meetings
Description | Date | Time | Particapants
Weekly scrum | 2023-08-28 | 11am | Luke, Henry, Brock
Weekly scrum | 2023-09-05 | 11am | Luke, Henry, Brock, Melanie
Weekly scrum | 2023-09-12 | 11am | Luke, Henry, Brock
Weekly scrum | 2023-09-25 | 3pm | Luke, Melanie, Brock
Weekly scrum | 2023-10-02 | 11am | Luke, Henry, Brock, Melanie
Weekly scrum | 2023-10-09 | 11am | Luke, Henry, Brock, Melanie
Weekly scrum | 2023-10-16 | 11am | Luke, Henry, Brock, Melanie
Weekly scrum | 2023-10-23 | 11am | Luke, Brock, Melanie
Weekly scrum | 2023-10-31 | 11am | Luke, Henry, Brock, Melanie
Weekly scrum | 2023-11-06 | 11am | Luke, Henry, Brock, Melanie
Weekly scrum | 2023-11-13 | 11am | Luke, Henry, Brock, Melanie
Weekly scrum | 2023-11-20 | 1pm | Luke, Henry, Brock, Melanie
Slack Calls
Description | Date | Time | Particapants | Duration
API Requirements | 2023-08-24 | 12pm | Henry, Brock | 40m
API key Information | 2023-08-30 | 10.30am | Henry, Brock | 60m
SEO pages | 2023-09-12 | 10am | Sam, Brock | 30m
API Key Utilisation | 2023-09-12 | 1pm | Henry, Brock | 40m
API Key Utilisation | 2023-09-12 | 3pm | Henry, Brock | 30m
API Acuity | 2023-09-13 | 11am | Henry, Brock | 40m
SEO pages, React, Tailwindcss | 2023-09-15 | 12pm | Luke, Brock | 90m
React, front-end and back-end setup | 2023-09-20 | 12pm | Luke, Brock | 1h 45m
SEO Redesign | 2023-09-25 | 11.15pm | Sam, Niamh, Brock | 30m
React assistance | 2023-09-26 | 1pm | Luke, Brock | 1h 45m
Pull Request | 2023-10-02 | 1.30pm | Henry, Brock | 50m
Extensions, Search results | 2023-10-04 | 3.30pm | Luke, Brock | 1h 55m
Worked on practitioner pages | 2023-10-13 | 9.45am | Henry, Brock | 1h50m
SEO API Requirements | 2023-10-16 | 2.20pm | Henry, Brock | 40m
Design feedback | 2023-10-24 | 9.30am | Niamh, Brock | 25m
Clinic API | 2023-10-24 | 2.30pm | Henry, Brock | 1h
Assessment Rubric and API work | 2023-10-25 | 10.50am | Henry, Brock | 1h 30m
API Work | 2023-10-27 | 4.20pm | Henry, Brock | 50m
Practitioner list details | 2023-10-27 | 2.30pm | Niamh, Brock | 15m
API Internal server error | 2023-10-31 | 1.45pm | Henry, Brock | 25m
Creating isValid checkers | 2023-11-03 | 10.30am | Luke, Brock | 1h 25m
Creating API calls for web pages | 2023-11-03 | 12.50pm | Henry, Brock | 2h 20m
Displaying sample data error | 2023-11-07 | 10.30am | Luke, Brock | 1h 40m
Business details page review | 2023-11-13 | 9.45am | Niamh, Brock | 15m
Continuing creation of APIs for clinic pages | 2023-11-14 | 3.40pm | Henry, Brock | 2h
Paired code review | 2023-11-15 | 11am | Luke, Brock | 4h 30m
Implementing real data | 2023-11-17 | 1pm | Henry, Brock | 30m
Final review | 2023-11-20 | 11.20am | Niamh, Brock, Luke | 20m
Scheduled Weekly Meetings
Description | Day | Time | Particapants
Developer Weekly Scrum meetings | Monday | 11am | Luke, Henry, Brock, Melanie
Class attendance | Monday | 3-5pm | David,Phillip , Brock
Weekly progress Meetings | Thursday | 12pm | Rob, Brock
Class attendance | Thursday | 1-3pm | David,Phillip , Brock

## Timetable
Weekly timetable
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Getting ready or free time
8-9am | [7 empty] | IND Work
9-10am | [7 empty] | AC Work/IND catchup
10-11am | [7 empty] | Class Attendance
11-12pm
12-1pm
1-2pm
2-3pm
3-4pm
4-5pm
6-7pm
7-8pm
8-9pm
9-10pm
10-11pm