## Sheet1
Project Title: | SEO Improvements and API Development |  | Start Date: | 2023-08-28
Project Client: | WellNow |  | Date Edited: | 2023-11-28
Deliverable | Step | Quality assurance task | Particapants | Compleation date
CV & Cover Letters | Academic 1 | Ara quality check 1 | Ara Career Centre | 2023-07-24
| Academic 2 | Ara quality check 2 | Ara Career Centre | 2023-08-15
| Academic 3 | Ara Tutor check | Phillip | 2023-08-15
Work Integrated Learning Agreement (WIL) | Academic 4 | Academic supervisor fill out | Robert | 2023-08-21
| Academic 5 | Course Convenor signing | David | 2023-08-21
Project Proposal | Academic 6 | Industry supervisor check | Henry | 2023-08-28
| Academic 7 | Academic supervisor check | Robert | 2023-09-06
| Academic 8 | Course Convenor check | David | 2023-09-07
Halfway Reports | Academic 9 | Industry supervisor check | Henry | 2023-10-12
| Academic 10 | Academic supervisor check | Robert | 2023-10-12
Summary Profile Document | Academic 11 | Profile Statement quality check 1 | Robert | 2023-09-28
| Academic 12 | Profile Statement quality check 1 | Sandy | 2023-09-28
Poster | Academic 13 | Poster initail design feedback | BCIS309 Class | 2023-11-09
| Academic 14 | Academic supervisor check | Robert | 2023-11-09
Final Report | Academic 15 | Academic supervisor check | Robert | 2023-11-24
| Academic 16 | APA References review | Library Learning Services | 2023-11-27
| Academic 17 | Academic supervisor check | Robert | 2023-11-28
| Academic 18 | Academic supervisor check | Robert | 2023-11-29
Methodology Essay | Academic 19 | Academic supervisor check | Robert | 2023-11-29
Weekly Scrum Meetings | Industry 1 | Weekly Meeting Attendance | Henry, Melanie, Luck | 2023-11-20
SEO Improvements | Industry 2 | HTML Review | Sam | 2023-09-12
| Industry 3 | React Initial Design Review | Niamh | 2023-09-25
| Industry 4 | Initail Bitbucket Pull Request | Henry, Luck | 2023-10-02
| Industry 5 | React Second Design Review | Niamh | 2023-10-03
| Industry 6 | FAQ Content Changes | Niamh | 2023-10-04
| Industry 7 | Practitioner List Details | Niamh, Brock | 2023-10-27
| Industry 8 | Business Details Page Review | Niamh, Brock | 2023-11-13
| Industry 9 | Code review | Luke | 2023-11-15
| Industry 10 | Final React Review | Niahm, Luck | 2023-11-20